## Implementation Guide
R&R PAYMENT AUTOMATION - IMPLEMENTATION GUIDE
PROJECT OVERVIEW
Duration | 2 Months (May-June 2026)
Total Budget | ₹157.73 Crores
Total Beneficiaries | 315
Target Phase 1 (May) | 75 beneficiaries
Target Phase 2 (June) | 150 beneficiaries
Remaining | 90 beneficiaries
SYSTEM REQUIREMENTS
Component | Specification | Purpose
Database | Excel/SQL Server | Store beneficiary & payment records
Dashboard | Web-based (HTML) | Real-time monitoring
Tracking System | Automated spreadsheet | Daily payment updates
Reporting | Excel reports | Weekly progress reports
Communication | Email automation | Notifications to stakeholders
AUTOMATED WORKFLOW PROCESS
Step | Action | System | Timeline
1 | Data Entry | Payment Tracking Sheet | Daily (morning)
2 | Verification | Automated checks | Daily (auto)
3 | Cheque Generation | System generates | Daily (11 AM)
4 | Distribution | Print & distribute | Daily (2 PM)
5 | Status Update | Mark as sent | Daily (4 PM)
6 | Dashboard Update | Real-time tracking | Continuous
7 | Report Generation | Auto reports | Weekly (Friday)
8 | Alert System | Notify blockers | Real-time
KEY PERFORMANCE INDICATORS (KPIs)
KPI | Target | Frequency | Owner
Disbursal Efficiency | 95-98% | Weekly | Finance
Processing Time | <5 days per beneficiary | Weekly | Admin
Document Readiness | >90% | Weekly | Verification
Cheque Clearing | >90% | Weekly | Bank
Payment Accuracy | 100% | Daily | Audit
On-time Payment | >95% | Weekly | Finance
RISK MANAGEMENT PLAN
Risk | Mitigation | Owner | Priority
Document delays | Pre-collect & verify docs | Verification | HIGH
Bank processing delay | Early submission to bank | Finance | HIGH
System downtime | Backup system in place | IT | MEDIUM
Payment errors | Multi-level validation | Audit | HIGH
Communication gaps | Weekly sync meetings | Project Lead | MEDIUM
TEAM ROLES & RESPONSIBILITIES
Role | Responsibility | Daily Task | Weekly Reporting
Project Lead | Overall coordination | Status check-in | Dashboard review
Finance Team | Payment processing | Generate cheques | Disbursal report
Verification Team | Document verification | Verify submissions | Completion report
Admin Team | Data entry | Update tracking sheet | Progress summary
IT Team | System maintenance | Monitor dashboard | System status