## Dashboard
R&R PAYMENT MONITORING DASHBOARD - 2 MONTH AUTOMATION
REAL-TIME PAYMENT STATUS (as of 23-Apr-2026)
Total Beneficiaries | 315 | Paid | 52 | Pending | 263
Total Disbursed | ₹52.35 Cr | Total Pending | ₹105.38 Cr | Avg/Beneficiary | ₹50.07 L
2-MONTH PAYMENT SCHEDULE PROGRESS
Week | Target Beneficiaries | Paid | Amount (₹ Cr) | Progress % | Status | Notes
Week 1 (May 1-7) | 20 | 18 | 10.5 | 90 | On Track | High priority beneficiaries
Week 2 (May 8-14) | 20 | 15 | 9.8 | 75 | On Track
Week 3 (May 15-21) | 20 | 12 | 8.2 | 60 | At Risk | Pending documents for 4
Week 4 (May 22-28) | 15 | 7 | 5.5 | 47 | At Risk
Week 5-8 (Jun 1-30) | 80 | 0 | 0 | 0 | Scheduled | Phase 2 disbursement
KEY PERFORMANCE INDICATORS
Metric | Value | Status | Notes
Disbursal Efficiency | 52/315 | 16.5% | Target: 25% by end Week 1
Average Processing Time | 4.2 days | Good | Per beneficiary
Document Completion Rate | 94% | On Track | 285 files ready
Cheque Status | 52 issued | Pending bank clearance | Est. 2-3 days
Pending Actions | 263 | Documents/Verification | Follow-up required
CRITICAL ACTIONS & BOTTLENECKS
Issue | Count | Impact | Action | Owner | Due Date
Missing Land Documents | 12 | High | Follow-up with beneficiaries | Verification Team | 03-May-2026
Pending Identity Verification | 8 | Medium | Fast-track verification | Admin | 02-May-2026
Bank Account Issues | 5 | High | Collect updated bank details | Finance | 04-May-2026
Option Form Not Received | 15 | Low | Send reminder notice | Field Team | 05-May-2026

## Summary Statistics
PAYMENT MONITORING - STATISTICAL SUMMARY
Metric | Current | Target (2 Months) | Achievement %
Total Beneficiaries | 315 | 315 | 10000%
Target to Pay (Week 1-4) | 75 | 75
Beneficiaries Paid | 52 | 75
Amount Disbursed (₹ Cr) | 52.35 | 100
Average Payment Per Person (₹ L) | 50.07 | 50.07 | 10000%
On-time Payment Rate % | 94 | 98
Document Completion % | 94 | 100
Cheques Cleared % | 88 | 95

## Automation Schedule
AUTOMATION WORKFLOW - 2 MONTH TIMELINE
Week | Date Range | Payment Phase | Automation Task | Expected Output | Status | Checklist
1 | 1-7 May | Phase 1 | Verify documents, Generate cheques | 52 cheques ready | ✓ In Progress | [ ] Docs verified [ ] Cheques printed
2 | 8-14 May | Phase 1 | Distribute cheques, Track delivery | Delivery confirmation | Scheduled | [ ] Distributed [ ] Confirmed
3 | 15-21 May | Phase 1 | Follow-up on pending cases | Status report | Scheduled | [ ] Issues resolved
4 | 22-28 May | Phase 1 | Reconciliation & closure | Month 1 report | Scheduled | [ ] Reconciled
5-8 | 1-30 Jun | Phase 2 | Process 150 more beneficiaries | 150 cheques | Scheduled | [ ] Phase 2 complete